## 3 Alpha Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Important Notes | Team's agreed upon schedule | The team should agree upon a schedule for when and where they will be meeting up outside of class time and document those times and places onto this card. |  |  |  |  | 3 | https://trello.com/c/cmgJADfQ
Important Notes | Code Freeze | Code freeze: A time when no changes whatsoever are permitted to the program's source code used to maintain and ensure the quality and integrity of the build. - Before each milestone and sprint end, a final integration is needed. - - Forces an integration at a safe time - - Ensures there is time for testing and validation of the build - - - Confirm sprint goals - - - Peer check each other’s work |  | 2023-01-17 17:00 |  |  | 13 | https://trello.com/c/kDhqqMtR
To Check (Peer) | Audio feedback on the menus [1] | Intent: - Inform the user that the input was entered | 1 |  | I,JR | TRC Requirement | 10 | https://trello.com/c/LnmNasH7
To Check (Peer) | Navigate the main menu | Intent: - Create functionality for the main menu Note on estimation: - This is generally a very quick task since it is just the functionality of the menu (not final visuals) |  |  | I,JR | TRC Requirement | 8 | https://trello.com/c/oX1jKHRD
To Check (Peer) | Background music for the menus and levels | Intent: - Create ambiance and emotional tone for the game and levels. |  |  | I | TRC Requirement | 11 | https://trello.com/c/xVN9tSN3
Incomplete | Camera shake | Intent: - Shaking the games camera in response to game events https://youtu.be/tu-Qe66AvtY |  |  | I | Difficulty: Low | 25 | https://trello.com/c/IaHiSVRp
Incomplete | Variable Jump | Intent: - Holding jump longer results in a higher jump. |  |  |  | Difficulty: Low | 22 | https://trello.com/c/KW9FrTQ5
Incomplete | Blocking | Holding up a defense that block all attacks coming from that direction | 1 |  | JR | Difficulty: Low | 29 | https://trello.com/c/DMalAoxl
Partially Complete | Weapon/Enemy Scaling [0.5] | Allows enemies to get stronger as the player gets into higher wave counts. Currently scales weapon pickups as well so that if a new weapon drops, it is not completely useless if picked up on a later wave where enemies are more tanky. | 0.5 |  | JR | Difficulty: Low | 41 | https://trello.com/c/40neBKfY
Partially Complete | Change options in the game | Intent: - Allow the end users to change the settings for music and SFX volume Note on implementation: - The easiest way to implement this is through setting up mixer groups and then routing the various audio sources in the game through the right mixer group (https://docs.unity3d.com/Manual/AudioMixer.html). An issue from mixer groups though is that they take volume in Db rather than a scaler 0 to 1 so it has to be converted. To roughly convert from a scaler value of 0-1 into logarithmic value for the unity mixer group is to use "Mathf.Log10(volume) * 20" Note on estimation: - Creating the menu doesn't take long. the difficulty and time involved on this one is in getting the mixer groups integrated in all of the audio sources in the game |  |  | I | TRC Requirement | 4 | https://trello.com/c/57RQChii
Partially Complete | Sniper [0.25] | Intent: - A slow firing enemy that deals massive damage. When the sniper is preparing to fire it will stop re-aiming at the target a visible laser will be rendered between the sniper and its target. | 2 |  | JR | Difficulty: Medium | 21 | https://trello.com/c/ShvPcUOq
Partially Complete | Essence Drop [5] | Intent: - Dead enemies drop items (usually spheres) that can be sucked up by the player to refill your health, magic, etc. | 3 |  | JR,DA | Difficulty: Low | 31 | https://trello.com/c/1jeWZHvl
Partially Complete | Knockback [1] | Pushing characters away from the source of damage | 1 |  | JR | Difficulty: Low | 16 | https://trello.com/c/Ytdhc9su
Partially Complete | Keyboard and mouse for the game's menus | Intent: - Create control structure allowing keyboard and mouse to be used for all of the game's menus Note on estimation: - Using the unity input system this should be very quick to accomplish if it hasn't been already. |  |  |  | TRC Requirement | 7 | https://trello.com/c/UmxEpHKG
Partially Complete | Projectiles for Enemies [1.5] | Enemies projectiles so that the player can take damage while also giving the player the ability to dodge enemy fire. | 2 |  | JR | Difficulty: Low | 15 | https://trello.com/c/qaZxPxuu
Partially Complete | Buy items in a shop [8.5] | A commerce system set up where the player can buy game items | 3 |  | JR,JW | Difficulty: Medium | 42 | https://trello.com/c/wYK7dX10
Partially Complete | Enemy Wave/Round Manager [8] | System to manage the spawning of enemies, downtime between rounds, and manage the amount of enemies that spawn over the course of the rounds. | 8 |  | JR,DA |  | 43 | https://trello.com/c/hA1ESbaI
Complete (Done) | Room Design |  | 8 |  | DA | Difficulty: Low | 35 | https://trello.com/c/jpJTX60k
Complete (Done) | Headshot Hitbox/Registration [1] | Allows players to deal extra damage to enemies via hitting critical/headshot hitboxes and locations? | 1 |  | JR | Difficulty: Low | 38 | https://trello.com/c/N7Womn3s
Complete (Done) | world props [3] |  | 3 |  | DA | Difficulty: Low | 36 | https://trello.com/c/p5ALgAnr
Complete (Done) | Sniper Rifle Scope Overlay [2.5] | Apply a scope overlay when scoping in with a sniper. Will do the 2D approach to avoid the issues with picture-in-picture (weird sensitivity + poor game performance). | 2 |  | JR | Difficulty: Medium | 37 | https://trello.com/c/n8ZIjIth
Complete (Done) | FPS guns going through walls fix [0.2] | Fix the bug where guns pass through environment objects This can easily be fixed by adding a second camera to the player that renders only the layer containing the player and the player's weapons/items https://youtu.be/wH4IyFXrWQw (the video references some URP flags but this works with the standard render pipeline as well by having a second camera and setting the clear flag on the gun camera to "depth only") | 0.5 |  | JR | Difficulty: Low | 39 | https://trello.com/c/6CVyyp1u
Complete (Done) | Showcase Level | A level that can be loaded with a debug menu button or debug key check that shows all of the created features in sequence. This would not be a level the users would ever see, just a space that proves the functionality works in an easily accessible way. This will be removed later for the final builds. |  |  |  |  | 12 | https://trello.com/c/52KnA6Ux
Complete (Done) | Sniper Rifle [0.5] | High damage and range but single shot and slow reload. | 0.5 |  | JR | Difficulty: Low | 18 | https://trello.com/c/92pdhDR7
Complete (Done) | Currency [0.5] | Intent: - Player can collect and spend curency | 0.5 |  | JR,DA,I,JW | Difficulty: Low | 17 | https://trello.com/c/cnTQBHwA
Complete (Done) | Ability to pause the game [1] | Intent: - Allow the user to stop playing the game momentarily | 1 |  | JR,DA,I,JW | TRC Requirement | 6 | https://trello.com/c/CFtYteDC
Complete (Done) | Damage Screen Effect [0.5] | An effect that shows up on the sides of the screen that shows when the player has taken damage | 0.5 |  | JR,DA,I,JW | Difficulty: Low | 23 | https://trello.com/c/jfGcoxwn
Complete (Done) | Health Pick up [1] | Intent: - An item that adds health to the player when picked up | 1 |  | DA | Difficulty: Low | 40 | https://trello.com/c/RHJ9K7Sf
Complete (Done) | Shotgun [1.5] | Strong damage with a good spread but very short range. | 1 |  | JR | Difficulty: Low | 20 | https://trello.com/c/0pmxFczX
Complete (Done) | Floor generation (Scraped) |  | 8 |  | DA | Difficulty: Medium | 34 | https://trello.com/c/fEEy6Gff
Complete (Done) | Player Melee Base Attacks | Basic attacks for the player |  |  | I,JR | Difficulty: Medium | 14 | https://trello.com/c/HcYW0wCz
Complete (Done) | Pick up dropping on death [1.5] | Intent: - Enemies sometimes dropping useful items when killed | 2 |  | JR | Difficulty: Low | 33 | https://trello.com/c/TCw8mtMJ
Complete (Done) | Aim Reticle/Cursor | A reticle that shows where the player is currently aiming? |  |  | JW | Difficulty: Low | 28 | https://trello.com/c/GH3zIi5j
Complete (Done) | Keyboard and mouse in-game | Intent: - Set up, test and use the default game controls for keyboard and mouse Note on estimation: - Using the unity input system this should be very quick to accomplish if it hasn't been already. |  |  |  | TRC Requirement | 9 | https://trello.com/c/vJzQJ3LH
Complete (Done) | Completion scenario (winning the game, achieving achievements, high score) | Intent: - Create the win condition and all of the experience we intend to provide with it Notes on estimation: - Creating the trigger for a win screen is very fast and easy, presenting the actual win scenario of the game can vary in difficulty and time necessary based on how what will be done when the player wins |  |  |  |  | 1 | https://trello.com/c/xp5SNmKx
Complete (Done) | Loss condition and it is clear to the user when and how they lost | Intent: - Create loss condition and player feedback involved in it |  |  |  |  | 2 | https://trello.com/c/TqoZJJeA
Complete (Done) | No warnings or errors in the code base | Intent: - Remove all warnings and errors from the product Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. People should be fixing warnings and errors as they develop their tasks. |  |  |  | TRC Requirement | 5 | https://trello.com/c/VJwiHmUo
Complete (Done) | Floating Damage Numbers [1] | Damaging an enemy shows the player how much damage was done | 1 |  | JR,JW |  | 44 | https://trello.com/c/pKYbviGV

## Archived 3 Alpha Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Important Notes | [archived] test | [5 empty] | 12 | https://trello.com/c/IAAmhHFM
Important Notes | [archived] test | [5 empty] | 13 | https://trello.com/c/sDL4XK7k