## 4 Beta Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Important Notes | Team's agreed upon schedule | The team should agree upon a schedule for when and where they will be meeting up outside of class time and document those times and places onto this card. |  |  |  |  | 15 | https://trello.com/c/KslcX5l6
Important Notes | Code Freeze | Code freeze: A time when no changes whatsoever are permitted to the program's source code used to maintain and ensure the quality and integrity of the build. - Before each milestone and sprint end, a final integration is needed. - - Forces an integration at a safe time - - Ensures there is time for testing and validation of the build - - - Confirm sprint goals - - - Peer check each other’s work |  | 2023-01-23 22:00 |  |  | 16 | https://trello.com/c/eeDWYgsA
Important Notes | Main Goals for Our Team | The main goals of our Alpha Sprint is getting the Quality-of-Life and gameplay loop elements done. That includes menu navigation feeling good, player is able to tell what is going on with waves and menus, etc. After that has been completed, if we have free time, we can move on to include any features possible that make the gameplay more fun and engaging. |  |  | JR | High Priority | 17 | https://trello.com/c/Amp7m74Y
Sprint Backlog (Beta) | Menu system final look and functionality | Intent: - Replace all placeholder assets with final ones - Ensure quality visuals throughout the product. |  |  |  |  | 7 | https://trello.com/c/T0Bwh8bt
Sprint Backlog (Beta) | Debug tools removal | Intent: - Finalizing the build to prepare for the quality assurance and submission process. Note on estimation: - Usually all this involves is commenting out the lines that trigger the debug functionality. This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. |  |  |  |  | 11 | https://trello.com/c/fz17AYAg
Complete (Done) | Experience the game without needing to have an additional player | Intent: - Ensure all players can experience a portion of the game without the need of an additional player on an online connection. Note on estimation: - This is mostly a verification at the end of the sprint and needs little if any time dedicated to it. If an entire new mode needs to be created to support this then there should be other cards defining that mode. |  |  | I,JR,JW,DA | TRC Requirement | 4 | https://trello.com/c/iP3dmGaj
Complete (Done) | Shotgun/Multi-shot Weapons [2] | Strong damage with a good spread but very short range. Also as a good framework for any other multi-shot weapons/abilities. | 1 |  | JR | Difficulty: Low | 19 | https://trello.com/c/JJ5Kk789
Complete (Done) | Play the game in a browser using WebGL | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Get the game online and playable in a browser if the game supports the web as its target platform. - If you end up having issues with memory limits this blog post goes into the details on that a bit https://blogs.unity3d.com/2016/09/20/understanding-memory-in-unity-webgl/ | 1 |  | JR | TRC Requirement,Target Platform | 6 | https://trello.com/c/64a4Cnwh
Complete (Done) | Floating Damage Numbers [2] | Damaging an enemy shows the player how much damage was done | 1 |  | JR,JW |  | 18 | https://trello.com/c/Dl2ByOx0
Complete (Done) | Enemy Wave/Round Manager [10] | System to manage the spawning of enemies, downtime between rounds, and manage the amount of enemies that spawn over the course of the rounds. | 8 |  | JR,DA | Difficulty: Low,Medium Priority | 6 | https://trello.com/c/ikizB1C8
Complete (Done) | Sounds for everything [8] | enemy actions, collecting things, interacting with things, triggering things… | 8 |  | I | High Priority | 16 | https://trello.com/c/aK58MJ4o
Complete (Done) | Projectiles for Enemies [2.5] | Enemies projectiles so that the player can take damage while also giving the player the ability to dodge enemy fire. | 2 |  | JR | Difficulty: Low,High Priority | 12 | https://trello.com/c/rW7cyA3Z
Complete (Done) | Installer for the game | Intent: - Create an installer for the product to make it easier to distribute. Note on estimation: - There should be little time needed to complete this task, An hour or two. Installers will be created using an installer creator application. | 0.5 |  | I,DA | TRC Requirement | 9 | https://trello.com/c/DtYwyClH
Complete (Done) | Identifiable icon | Intent: - Allow users to easily recognize the game from its icon image Note on estimation: - There should be very little time needed to complete this task. Adding an icon tot he game's exe using unity involves a drag and drop in the player settings. | 2 |  | I,DA,JR,JW | TRC Requirement | 8 | https://trello.com/c/Gw119ob2
Complete (Done) | Play the game without needing to enable administrator mode | Intent: - Allow a larger user base by ensuring users do not need administrator access to the player the game after installation. Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. If the exe build did not ask for admin rights after saving was created on the last sprint it is unlikely that this will become an issue now. | 1 |  | I,DA,JR,JW | TRC Requirement | 2 | https://trello.com/c/QZoqWc2E
Complete (Done) | No warnings or errors in the code base [1] | Intent: - Remove all warnings and errors from the product Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. People should be fixing warnings and errors as they develop their tasks. ‌ | ? |  | I,DA,JR,JW | TRC Requirement | 12 | https://trello.com/c/tdy7GjFE
Complete (Done) | Keyboard and mouse for the game's menus [1.5] | Intent: - Create control structure allowing keyboard and mouse to be used for all of the game's menus Note on estimation: - Using the unity input system this should be very quick to accomplish if it hasn't been already. | 1 |  | I | TRC Requirement,High Priority | 4 | https://trello.com/c/jbV7bFGz
Complete (Done) | Controls to function and be comfortable when playing the game on the WebGL build | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Customize the controls to be fully usable on web builds if the game supports the web player as its target platform. | 1 |  | I,JR | TRC Requirement,Target Platform | 5 | https://trello.com/c/iYgXXXNX
Complete (Done) | Maintain a frame rate of at least 30 frames per second | Intent: - Maintain a smooth and clear game experience Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. If however the game is already having issues with framerate at the point of estimating this card then the team should make their best judgement on the time to optimize where they think the slowdowns are located. | 1 |  | I,DA,JR,JW | TRC Requirement | 3 | https://trello.com/c/BHPyR5eE
Complete (Done) | Buy items in a shop [13] | A commerce system set up where the player can buy game items | 3 |  | JR,JW | Difficulty: Medium,Medium Priority | 13 | https://trello.com/c/0pltsUNF
Complete (Done) | Credits (everyone who contributed to creating the game to get credit for their work) | Intent: - Credit everyone who contributed to the product - For outsourced assets from web portals give enough information to be able to find the source of the asset (“Asset Name by AuthorName from website.com”) Note on estimation: - Time to complete this task is heavily dependent on if we have been maintaining a list of where we got our assets from or if we need to spend time to re-find the source of the assets. | 3 |  | I | TRC Requirement | 10 | https://trello.com/c/wxNTPSNx
Complete (Done) | Weapon Upgrade Feedback | Let’s the player know what has changed with a weapon when it has upgraded | 1.5 |  | JW | Difficulty: Low,High Priority | 10 | https://trello.com/c/ejZ5LJzC
Complete (Done) | Visible trails behind bullets [2] | Intent: - Bullets leave a small mostly transparent like behind the bullet representing its wake in the air. | 1 |  | JR | Difficulty: Low,High Priority | 7 | https://trello.com/c/ItfiRt2h
Complete (Done) | Change options in the game [8] (settings) | Intent: - Allow the end users to change the settings for music and SFX volume Note on implementation: - The easiest way to implement this is through setting up mixer groups and then routing the various audio sources in the game through the right mixer group (https://docs.unity3d.com/Manual/AudioMixer.html). An issue from mixer groups though is that they take volume in Db rather than a scaler 0 to 1 so it has to be converted. To roughly convert from a scaler value of 0-1 into logarithmic value for the unity mixer group is to use "Mathf.Log10(volume) * 20" Note on estimation: - Creating the menu doesn't take long. the difficulty and time involved on this one is in getting the mixer groups integrated in all of the audio sources in the game | 2 |  | I,JR | TRC Requirement,High Priority | 11 | https://trello.com/c/z9DnXBow
Complete (Done) | Weapon/Enemy Scaling | Allows enemies to get stronger as the player gets into higher wave counts. Currently scales weapon pickups as well so that if a new weapon drops, it is not completely useless if picked up on a later wave where enemies are more tanky. |  |  | JR | Difficulty: Low | 3 | https://trello.com/c/otPhnSRS
Complete (Done) | Melee Weapon feedback [5] | Melee Weapon feedback is even more needed as it is completely static and doesn’t show the range Animation for swinging? trail for swing? | 5 |  | I | High Priority,Difficulty: Medium | 15 | https://trello.com/c/3FTvljEP

## Archived 4 Beta Sprint
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Sprint Backlog (Beta) | [archived] Play the game using an android device | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Make the game playable on an android tablet If the game supports the tablet as its target platform. - If you have not already installed the packages necessary to export android build you can follow the directions how to do so here https://www.youtube.com/watch?v=4YNH9Y7NR3U |  |  |  | TRC Requirement,Target Platform | 13 | https://trello.com/c/QPQ8uQYV
Sprint Backlog (Beta) | [archived] Controls function and be comfortable when playing the game on an android device | This is only applicable if this is the intended secondary target platform. If the team is going with a different secondary platform this card can be archived. Intent: - Customize the player controls for a touch-based device if the game supports the tablet as its target platform. |  |  |  | TRC Requirement,Target Platform | 14 | https://trello.com/c/cIEr2sjp
Sprint Backlog (Beta) | [archived] Game can be played on any monitor/TV set | Intent: - Allow the game to be played on any monitor/TV set. This is testing for screen bounds images sizes and aspect ratios Note on Implementation: - Other that HUD layout, having canvas scaler components handling how each screen scales to fit aspect ratios is the main things that needs to be done to support this. Note on estimation: - This is mostly a verification at the end of the sprint and usually needs little if any time dedicated to it unless there are currently known issues. | 1 |  | I,DA,JR,JW | TRC Requirement | 1 | https://trello.com/c/Bn66imac
Sprint Backlog (Beta) | [archived] Camera shake | Intent: - Shaking the games camera in response to game events https://youtu.be/tu-Qe66AvtY | 5 |  | I | Difficulty: Low | 1 | https://trello.com/c/uRPEbBia
Sprint Backlog (Beta) | [archived] Blocking | Holding up a defense that block all attacks coming from that direction | 1 |  | JR | Difficulty: Low | 2 | https://trello.com/c/ud0JcyCG
Sprint Backlog (Beta) | [archived] Change options in the game | Intent: - Allow the end users to change the settings for music and SFX volume Note on implementation: - The easiest way to implement this is through setting up mixer groups and then routing the various audio sources in the game through the right mixer group (https://docs.unity3d.com/Manual/AudioMixer.html). An issue from mixer groups though is that they take volume in Db rather than a scaler 0 to 1 so it has to be converted. To roughly convert from a scaler value of 0-1 into logarithmic value for the unity mixer group is to use "Mathf.Log10(volume) * 20" Note on estimation: - Creating the menu doesn't take long. the difficulty and time involved on this one is in getting the mixer groups integrated in all of the audio sources in the game | 3 |  | I | TRC Requirement,High Priority | 5 | https://trello.com/c/1JwilMY1
Sprint Backlog (Beta) | [archived] Stun after damage | A character that is damaged will have a moment where they don't take actions in response to the damage | 1 |  | JR | Difficulty: Low,Low Priority | 8 | https://trello.com/c/b0fP351R
Sprint Backlog (Beta) | [archived] Indicators for Waves UI | Let’s the play know when a wave has ended and when a wave starts | 1 |  | DA | Difficulty: Low,High Priority | 9 | https://trello.com/c/v1DAnEgp
Sprint Backlog (Beta) | [archived] Replacing Placeholder Assets | Any placeholder assets are to be replaced with assets (i.e. Unity Store) |  |  |  | TRC Requirement | 14 | https://trello.com/c/Ne6dMt3e